## Sheet1
Consolidated GRC Gap Assessment
Gap ID | Framework(s) | Current State | Desired State | Severity | Owner | Target
GAP-01 | ISO, CSF | Monitoring coverage inconsistent; no MTTD metric | Full coverage, MTTD tracked monthly | Critical | IT Operations | 30 days
GAP-02 | ISO, CSF | Incident response plan never exercised | Annual tabletop completed and evidenced | High | CISO | 90 days
GAP-03 | ISO | 15 of 25 SoA controls not yet operational | All controls implemented | Medium | GRC Manager | 6 months
GAP-04 | Enterprise | Shadow IT not systematically discovered | Automated discovery tooling deployed | Medium | IT Operations | 6 months
GAP-05 | Enterprise | Cross-border data practices not formally mapped | Data mapping complete, mechanisms documented | High | Legal / GRC Manager | 90 days
GAP-06 | RMF (GSP) | 1 of 3 POA&M findings still open | All POA&M items closed and verified | High | IT Ops / Network Eng. | 30-90 days