## Sheet1
Risk Treatment Plan: VertexOne Digital Services
Priority | Item | Treatment | Owner | Target
Critical | GAP-01 Monitoring coverage | Mitigate : extend SIEM, define MTTD | IT Operations | 30 days
High | GAP-02 Untested incident response | Mitigate : run tabletop exercise | CISO | 90 days
High | GAP-05 Cross-border data exposure | Mitigate : complete data mapping | Legal / GRC Manager | 90 days
High | GAP-06 GSP POA&M closure | Mitigate : clear patch backlog | IT Operations | 30 days
Medium | GAP-03 Remaining SoA controls | Mitigate : complete Phase 2/3 rollout | GRC Manager | 6 months
Medium | GAP-04 Shadow IT discovery | Mitigate : deploy discovery tooling | IT Operations | 6 months
Low (monitor) | R-004, R-010, R-012, R-015 | Accept/Monitor : already effectively treated | Respective owners | Ongoing