## Sheet1
Control Implementation Tracker : VertexOne Digital Services
Control | Phase | Target Date | Status | % Complete | Blocking Issues
A.8.5 Secure Authentication | 1 | 30 days | In Progress | 40% | Legacy accounts pending MFA rollout
A.8.2 Privileged Access Rights | 1 | 30 days | In Progress | 50% | Awaiting privileged account inventory completion
A.8.8 Vulnerability Management | 1 | 30 days | In Progress | 35% | Dependency scanning tool licensing in procurement
A.8.9 Configuration Management | 1 | 30 days | Not Started | 0% | Automated scanning tool not yet selected
A.8.13 Backup | 1 | 30 days | In Progress | 60% | Restoration test schedule not yet finalized
A.8.25 Secure Development Life Cycle | 1 | 30 days | Not Started | 0% | SDLC policy draft pending Engineering Lead review
A.5.19 Supplier Relationships | 2 | 60 days | Not Started | 0% | Legal review capacity constrained
A.6.3 Awareness & Training | 2 | 60 days | Not Started | 0% | LMS vendor selection pending
A.5.30 Business Continuity Readiness | 3 | 90 days | Not Started | 0% | Dependent on backup testing completion (A.8.13)