## Sheet1
Risk Treatment Plan : VertexOne Digital Sevices
Risk ID | Treatment | Planned Action | Owner | Target Date | Priority
R-002 | Mitigate | Implement WAF rules and conduct secure code review of legacy portal modules | Engineering Lead | Within 30 days | 1 (Highest)
R-001 | Mitigate | Complete full dependency scanning coverage; enforce critical patch SLA of 15 days | CISO / Engineering | Within 45 days | 2
R-004 | Mitigate | Enforce MFA for all users, not only administrators | CISO | Within 30 days | 3
R-006 | Mitigate | Deploy EDR to ERP host; disable and rotate default credentials | IT Operations | Within 60 days | 4
R-007 | Mitigate | Automate offboarding deprovisioning workflow between HR and IT systems | HR / IT Operations | Within 60 days | 5
R-003 | Mitigate | Enforce least-privilege access policies; enable automated configuration scanning | IT Operations | Within 45 days | 6
R-008 | Mitigate | Complete secrets management rollout; harden pipeline access controls | Engineering Lead | Within 60 days | 7
R-015 | Mitigate | Implement immutable backup storage; schedule quarterly restoration testing | IT Operations | Within 90 days | 8
R-005 | Mitigate | Roll out organization-wide security awareness training; enforce DMARC | GRC Manager / HR | Within 90 days | 9
R-009 | Mitigate | Deploy EDR fleet-wide; enforce VPN for remote access | IT Operations | Within 90 days | 10
R-012 | Transfer + Mitigate | Add security clause to vendor contract; confirm cyber insurance coverage | Legal / GRC Manager | Within 60 days | 11
R-010 | Mitigate | Implement quarterly repository access reviews and branch protection rules | Engineering Lead | Within 90 days | 12
R-011 | Mitigate | Implement formal identity verification protocol for support requests | Support Manager | Within 90 days | 13
R-013 | Mitigate | Conduct formal vendor security assessment | HR / Legal | Within 90 days | 14
R-014 | Accept | No further action; monitor via annual facilities review | Facilities / IT Operations | N/A | Monitor only
Document | Risk Treatment Plan
Organization | VertexOne Digital Services
Prepared By | Junior GRC Analyst
Status | Draft for Risk Committee Approval
Purpose | Define actions required to treat identified information security risks
Priority Method | Priority 1 represents the highest treatment priority