## Sheet1
Statement of Applicability (SoA): VertexOne Digital Services
Per ISO/IEC 27001:2022 Clause 6.1.3(d). Selected controls are justified against the Risk Register (R-001-R-015) established on Day 2.
Control | Selected? | Related Risk(s) | Justification | Owner | Status
A.5.15 Access Control | Yes | R-004, R-007 | Governs who can access sensitive systems and data | CISO | In Progress
A.5.16 Identity Management | Yes | R-004 | Manages identity lifecycle to prevent orphaned or excessive access | CISO | In Progress
A.5.17 Authentication Information | Yes | R-004 | Governs password and credential handling | CISO | Not Started
A.5.19 Supplier Relationships | Yes | R-012, R-013 | Addresses missing vendor security clauses and assessments | Legal / GRC Manager | Not Started
A.5.23 Cloud Services Security | Yes | R-003, R-004, R-005 | Defines shared-responsibility expectations for Azure/M365 | IT Operations | In Progress
A.5.24 Incident Management Planning | Yes | All | Establishes response process for any risk that materializes | CISO | Not Started
A.5.30 ICT Readiness for Business Continuity | Yes | R-015 | Ensures recovery capability for backup/DR risk | IT Operations | Not Started
A.5.36 Compliance with Policies & Standards | Yes | All | Verifies ongoing conformance to internal policy | GRC Manager | In Progress
A.6.3 Awareness, Education & Training | Yes | R-005, R-009 | Addresses inconsistent regional security awareness | HR / GRC Manager | Not Started
A.6.5 Responsibilities After Termination | Yes | R-007 | Addresses orphaned account risk from inconsistent offboarding | HR | Not Started
A.7.2 Physical Entry | Yes | R-014 | Existing badge access control for office premises | Facilities | Implemented
A.7.9 Security of Assets Off-Premises | Yes | R-009 | Governs security of endpoints used by remote workforce | IT Operations | Not Started
A.8.1 User Endpoint Devices | Yes | R-009 | Standardizes endpoint security configuration | IT Operations | In Progress
A.8.2 Privileged Access Rights | Yes | R-004 | Restricts and monitors elevated access | CISO | In Progress
A.8.5 Secure Authentication | Yes | R-004 | Enforces MFA to address credential theft risk | CISO | In Progress
A.8.7 Malware Protection | Yes | R-006, R-009 | Addresses ransomware/malware threats to ERP and endpoints | IT Operations | Not Started
A.8.8 Management of Technical Vulnerabilities | Yes | R-001, R-002 | Addresses unpatched dependencies on customer-facing systems | Engineering Lead | In Progress
A.8.9 Configuration Management | Yes | R-003, R-006 | Prevents misconfiguration of cloud storage and ERP systems | IT Operations | Not Started
A.8.12 Data Leakage Prevention | Yes | R-003 | Reduces risk of customer data exposure | IT Operations | Not Started
A.8.13 Backup | Yes | R-015 | Ensures data recoverability against ransomware | IT Operations | In Progress
A.8.16 Monitoring Activities | Yes | R-006 | Improves detection capability on the legacy ERP system | IT Operations | Not Started
A.8.24 Use of Cryptography | Yes | R-003, R-010 | Protects data at rest and source code confidentiality | Engineering Lead | Not Started
A.8.25 Secure Development Life Cycle | Yes | R-002, R-008 | Reduces vulnerabilities introduced during development | Engineering Lead | Not Started
A.8.28 Secure Coding | Yes | R-002 | Directly addresses input validation gaps in the customer portal | Engineering Lead | Not Started
A.8.29 Security Testing in Development | Yes | R-002, R-008 | Validates fixes before release to production | Engineering Lead | Not Started
A.7.4 Physical Security Monitoring | No | R-014 | R-014 is a formally accepted Low residual risk; existing badge control is proportionate | - | Not Applicable
A.7.6 Working in Secure Areas | No | - | VertexOne's hybrid office model has no designated secure physical zones | - | Not Applicable
A.8.30 Outsourced Development | No | - | All software development is performed in-house | - | Not Applicable
Prepared by: Junior GRC Analyst