## Sheet1
CAPA Tracker
Finding | Stage | Verification Evidence | Status
F-001 | Closure Verified | Restoration test report (RTO/RPO met); updated Document Control Procedure | Closed
F-005 | Closure Verified | 8 consecutive weeks of complete scan logs | Closed
F-002 | Closure Verified | Review sign-off; active recurring reminder confirmed | Closed
F-003 | Monitoring | Completion at 89%, up from 68-72%; target 95% | Open — trending correctly
F-004 | Closure Verified | All 4 vendor addenda signed and filed | Closed