## Sheet1
Corrective Action Plan : VertexOne Digital Services
Finding | Root-Cause-Level Corrective Action | Owner | Target Date | Status | Effectiveness / Monitoring
F-001 | Complete first backup restoration test; update Document Control Procedure to require owner sign-off on all new procedures | IT Operations / GRC Manager | Closed | Closed | -
F-005 | Configure automated missed-scan alerting; assign accountable weekly reviewer | Engineering Lead | Closed | Closed | -
F-002 | Complete overdue review; re-establish recurring calendar reminder | IT Operations | Closed | Closed | -
F-003 | Implement manager escalation at 30 days overdue for training completion | HR | Closed | Closed | Effectiveness partial; monitoring continues
F-004 | Complete remaining 2 vendor security addenda | Legal | Closed | Closed | -
Document | CORRECTIVE ACTION PLAN
Organization | VertexOne Digital Services
Prepared By | Junior GRC Analyst
Approved By | CISO
Overall Status | Approved
Purpose | Track root-cause-level corrective actions arising from audit findings