## Sheet1
NIST CSF Gap Assessment: VertexOne Digital Services
Function | Current State | Target State | Gap | Business Risk | Priority | Recommended Action | Evidence / Measure | Owner | Target Date | Status
GOVERN | Addenda in place, untiered | Tiered vendor risk reporting | No criticality-based vendor tiering | Legal review effort spread evenly regardless of actual risk concentration | Medium | Implement vendor criticality tiers and establish risk-based supplier reporting | Vendor tiering matrix; supplier risk report; Management Review minutes | Third-Party Risk Manager | Q4 2026 | Open
IDENTIFY | Manual annual asset review | Near-continuous discovery | No automated discovery tooling | Shadow cloud resources could go unassessed between review cycles | Medium | Deploy automated asset discovery across cloud and enterprise environments | Automated asset inventory; discovery reports; exception records | IT Asset Manager | Q1 2027 | Open
PROTECT | 89% awareness; manual configuration checks | 95%+ awareness; automated configuration scanning | Awareness below target; configuration scanning not automated | Elevated human-layer and misconfiguration risk | High | Increase awareness completion to 95%+ and deploy automated cloud configuration monitoring | Training completion report; configuration drift reports | CISO / Security Operations | Q1 2027 | Open
DETECT | Partial monitoring coverage; no MTTD metric | Full critical-asset coverage; MTTD tracked monthly | Legacy system blind spot; no detection performance measurement | Delayed detection of a real compromise | Critical | Extend SIEM monitoring to legacy systems and establish monthly MTTD reporting | SIEM coverage report; MTTD dashboard; monthly metrics | Security Operations Manager | Q4 2026 | Open
RESPOND | Documented plan; never tested | Annual tested tabletop exercise | No incident response exercise performed | Unknown whether the response plan works under pressure | High | Conduct annual incident response tabletop exercise and document lessons learned | Tabletop exercise report; attendance record; lessons-learned register | Incident Response Manager | Q1 2027 | Open
RECOVER | Restoration tested; communication untested | Both tested together each cycle | Recovery communication plan unverified | Confusion or delay in stakeholder communication during a real recovery | Medium | Test recovery communications alongside backup restoration exercises and document lessons learned | Recovery test report; communication test record; lessons-learned register | Business Continuity Manager | Q1 2027 | Open