## Sheet1
NIST CSF Improvement Roadmap
Action ID | Function | Improvement Action | Priority | Timeframe | Owner | Supporting Functions | Success Measure | Evidence / Deliverable | Dependency | Status
IR-001 | DETECT | Extend SIEM and monitoring coverage to the legacy ERP system | Critical | 0-30 Days | IT Operations | Security Operations; Engineering Lead | 100% monitoring coverage for critical ERP assets | SIEM coverage report; monitoring configuration | None | Open
IR-002 | DETECT | Define Mean Time to Detect (MTTD) metric and begin monthly tracking | Critical | 0-30 Days | Security Operations | GRC Manager | MTTD metric formally defined and reported monthly | MTTD dashboard; monthly security metrics | IR-001 | Open
IR-003 | RESPOND | Conduct the first incident response tabletop exercise | High | 90 Days | IT Operations | GRC Manager; Security Operations; Legal | Tabletop exercise completed and lessons learned documented | Tabletop exercise report; attendance record; lessons-learned register | IR-001 | Open
IR-004 | PROTECT | Complete the current security awareness training escalation cycle toward the 95% target | High | 90 Days | HR | GRC Manager; IT Operations | Awareness completion reaches at least 95% | Training completion report; escalation records | None | Open
IR-005 | PROTECT | Automate configuration drift scanning across all cloud environments | High | 6 Months | Engineering Lead | IT Operations; Security Operations | Automated configuration drift monitoring operational across all cloud environments | Configuration drift reports; monitoring dashboard | None | Open
IR-006 | GOVERN | Tier vendor security questionnaires and reporting by criticality | Medium | 6 Months | Legal | GRC Manager; Procurement | All critical vendors assigned risk tiers and reported accordingly | Vendor risk-tiering matrix; supplier risk report | None | Open
IR-007 | IDENTIFY | Implement near-continuous asset discovery, including shadow cloud resources | Medium | 12 Months | IT Operations | Engineering Lead; Security Operations | Automated asset discovery operating across in-scope environments | Asset discovery reports; updated asset register | None | Open
IR-008 | RECOVER | Test the recovery communication plan alongside the next scheduled restoration test | Medium | 12 Months | IT Operations | GRC Manager; Business Continuity | Recovery communication plan successfully tested and lessons learned documented | Recovery test report; communication test record; lessons-learned register | Next restoration test | Open
IR-009 | GOVERN | Complete full NIST CSF Profile reassessment | Critical | 12 Months | GRC Manager | CISO; Control Owners | Current and Target Profiles reassessed and gaps updated | Updated CSF Current Profile; Target Profile; Gap Assessment | IR-001 to IR-008 | Open