## Sheet1
NIST CSF Risk Prioritization Matrix
Priority | Function | Gap | Rationale | Risk Impact | Recommended Treatment | Dependency | Target Sequence | Status
Critical | DETECT | Coverage gap + no MTTD metric | Foundational — weak detection undermines RESPOND and RECOVER even where those functions otherwise perform well | High | Extend monitoring to all critical assets including legacy systems and establish monthly MTTD reporting | None | 1 | Open
High | PROTECT | Awareness below target | Directly reduces phishing and social engineering exposure; closable within one additional training cycle | High | Increase security awareness completion to 95%+ and monitor completion monthly | None | 2 | Open
High | RESPOND | No tested incident response plan | Unverified response capability is a significant unknown risk with relatively low cost to close through a tabletop exercise | High | Conduct annual incident response tabletop exercise and document lessons learned | DETECT improvements support response validation | 3 | Open
Medium | GOVERN | Untiered vendor risk | Functioning process exists; improvement is needed to focus oversight on higher-risk suppliers | Medium | Implement vendor criticality tiers and include supply chain risk reporting in Management Reviews | Vendor inventory | 4 | Open
Medium | IDENTIFY | Manual-only asset discovery | Existing manual process functions; automation is primarily a coverage and efficiency improvement | Medium | Implement automated asset discovery and identify unmanaged or shadow cloud resources | Cloud and enterprise asset inventory | 5 | Open
Medium | RECOVER | Untested recovery communication | Core recovery capability is already strong because restoration is tested; communication requires validation | Medium | Test the recovery communication plan alongside each restoration exercise and record lessons learned | Backup restoration testing | 6 | Open