## Sheet1
NIST CSF Current Profile | [5 empty] | NIST CSF Target profile
Function | Current State | Evidence / Reference | Key Strength | Key Gap / Observation | Assessment Status | Function | Target State | Target Evidence / Measure | Target Objective | Priority | Timeframe | Status
GOVERN | Policy, RACI, and Management Review formally established; vendor security addenda in place for all critical vendors | Policies; RACI Matrix; Management Review Records; Vendor Security Addenda | Formal governance structure and vendor oversight established | No significant gap identified | Established | GOVERN | Vendor security risk tiered by criticality; supply chain risk formally reported at every Management Review | Vendor risk tiers; supplier risk reports; Management Review minutes | Strengthen third-party and supply chain risk governance | High | 12 Months | Target
IDENTIFY | Asset and risk registers complete and reviewed annually; 15 risks assessed (R-001 to R-015) | Asset Register; Risk Register R-001 to R-015 | Asset and risk identification processes established | Annual review cadence may require event-driven updates | Established | IDENTIFY | Near-continuous asset discovery, including shadow cloud resources, supplementing the annual manual review | Automated asset discovery reports; cloud inventory; discovery logs | Improve visibility of organizational assets and unmanaged resources | High | 12 Months | Target
PROTECT | MFA at 100%, EDR deployed fleet-wide, awareness training at 89% and improving, encryption enabled on customer data at rest | MFA Evidence; EDR Deployment Records; Training Records; Encryption Configuration | Strong preventive security controls implemented | Awareness training remains below 100% | Mostly Established | PROTECT | 95%+ sustained awareness completion; automated configuration drift scanning live across all cloud environments | Training completion reports; configuration drift reports; cloud security monitoring | Increase workforce security awareness and reduce cloud configuration risk | High | 12 Months | Target
DETECT | SIEM deployed with daily alert triage; coverage gap remains on the legacy ERP system; no mean-time-to-detect metric currently tracked | SIEM Records; Alert Triage Logs; Monitoring Evidence | Continuous SIEM monitoring and daily alert triage established | Legacy ERP monitoring gap; MTTD metric not currently tracked | Partially Established | DETECT | Full monitoring coverage across all critical assets including legacy systems; mean-time-to-detect tracked and reported monthly | SIEM coverage reports; monitoring dashboards; monthly MTTD reports | Eliminate critical monitoring gaps and establish measurable detection performance | Critical | 12 Months | Target
RESPOND | Incident response plan documented with a defined escalation path; has never been exercised via tabletop simulation | Incident Response Plan; Escalation Matrix | Formal incident response process documented | No tabletop exercise performed to validate response capability | Partially Established | RESPOND | Annual incident response tabletop exercise completed; communication plan validated against a simulated scenario | Tabletop exercise report; lessons learned; communication validation records | Validate incident response and communication effectiveness | High | 12 Months | Target
RECOVER | Backup restoration tested quarterly with documented RTO/RPO; recovery communication plan remains untested | Backup Restoration Test; RTO/RPO Results; Recovery Plan | Regular restoration testing and documented recovery objectives | Recovery communication plan has not been tested | Partially Established | RECOVER | Recovery communication plan tested alongside each restoration test; lessons learned formally logged every cycle | Recovery test reports; communication test records; lessons-learned register | Improve recovery coordination and continuous improvement | Medium | 12 Months | Target