## Sheet1
Corrective Action Register_CAPA
Finding ID | Corrective Action | Owner | Deadline | Verification Method
F-001 | Complete first backup restoration test | IT Operations | 30 days | GRC Manager reviews completed test report and RTO/RPO results
F-002 | Complete overdue privileged access review; fix recurring reminder | IT Operations | 15 days | GRC Manager confirms completed review and corrected calendar entry
F-003 | Implement manager escalation at 30 days overdue; re-measure completion | HR | 60 days | HR provides updated regional completion report
F-004 | Complete remaining 2 vendor security addenda | Legal / GRC Manager | 60 days | GRC Manager confirms signed addenda filed in contract repository
F-005 | Configure automated missed-scan alerting; backfill missed weeks | Engineering Lead | 20 days | GRC Manager confirms 8 consecutive weeks of complete scan logs